| GOAL: To create an E-LEARNING environment |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTIONS | 2010 - Key Tasks |  |  |  |
|  | Term 1 | Term 2 | Term 3 | Term 4 |
| - Use I.C.T to enhance & consolidate literacy and Numeracy practises across the school | - IT Cluster survey - Staff Survey – Diane and Andrew to develop – list sch resources - 24th March staff meeting. - KWS survey –What would I like to try? - Useful resources/sharing - Determine goals for IT. | - Staff visit to Ohaeawai /Morningside Lit / Num focus. - Staff sharing day with the involvement of the BOT. Visits across the cluster. - Teachers to set personal goals as part of the appraisal process. | - Each teacher to have 2 timetabled session with Dianne focusing on their appraisal goal. |  |
| - To develop an inquiry model that meets the needs of our students – authentic, student centred learning. |  | - Investigate inquiry models from other schools – eg. - Coley St - Pakaraka | - Introduce an inquiry model (Kath Murdoch)to staff for term three topic focusing on the new school vision | - Create an overview for the 2011 incorporating student voice.(James Beane) |
| - Enhance school wide systems that enable teachers to reduce and manage work load through the use of I.C.T | - Undertake training with Scottronics for leaders and admin staff. - T.O.D sharing conference ideas and introduce calendar for staff. | - School Calendar - E -tap training – Attendance Registers, Assessment – data entry. - Investigate ICT into assemblies. - ETAP training with Rob Webb 14 May. | - Reporting to parents through conferences. |  |
| - Create effective learning communities between schools, within schools and the wider community | - Conference - 1 x LT day - TOD 16th April 1-3pm breakouts - Wikispaces page - L.Ts meeting to share. | - Create an opportunity for the lead teacher to be using IT in the classroom. Modelling. |  |  |
| - provide resources to support ICT development | - Purchase new cameras and video cameras. - Develop ICT lead teacher job description. | - New Interactive whiteboard for lead teacher in room 5. - New sound system to support teachers at assembly, school visits etc. | - Investigate the implementation of 2 new boards into the school. One into the bilingual unit and one mainstream. Tendering [process used to identify new teachers. |  |
| - Budget costs | - Conference - Cameras - Calendar training | - Sound system - Rm 5 Board - E tap training | - 2 new interactive boards |  |