Milestone 1 2010 Template                            Kai-oro-hoki

| Milestone Number : | 1 |
| --- | --- |
| Cluster Name | Kai-oro-hoki |
| Contract Number | 10-0239 |
| Lead School | Kaikohe Intermediate |
| MoE School ID Number | 1022 |
| Date | 4th June 2010 |
| National Facilitator | Kathe Tawhiwhirangi |
| Project Director/s | Phil Gordon and Chicky Rudkin |
| Facilitator/s | Diane Henderson |

Milestone 1

1. Response to Milestone tasks

1.2 Details of the tasks to be completed by the contractor to achieve this milestone are:

1.2.1 Liaise with the National Facilitator assigned to this project;

| What did we do? | Who was involved? | What was the outcome? |
| --- | --- | --- |
| Informal mtgs @ L@S Conference | Principals Annie -and some lead teachers Facilitator | · Discussions around the content of some workshops · The overflow of the Keynote room and the timing of the start of these · TKI session and the ease at which Te Reo can flow into classrooms with this technology |
| Emails / Google Docs | Facilitator – Diane Henderson Acting PD – Chicky Rudkin | · Discussions around expected outcomes and possibilities re baseline data, lining up the Nat goals, cluster goals & school goals with school and teacher action plans Discussions re budget / finance for conferences / school payments Regular updates and feedback using Google Docs Use of google docs to do milestone reporting |
| Northland Cluster Network mtg | Management team, PF & Lead teachers (x 9) | · Possibilities in regard to tracking expenses, effectiveness of PF’s, possibilities for infusing ICT’s in to the classrooms after the walk through, ideas gleaned from the other clusters Sharing of what is happening for our cluster Ideas for our cluster sharing day 24th Sept. |
| Meeting Face to face – Wednesday 21st April | Facilitator – Diane Henderson Project Director - Phil Gordon - Kaikohe Intermediate Principals- Kaikohe East – Chicky Rudkin Kaikohe West – Hamish Ruawai Okaihau Primary – Tim Couling Tautoro Primary – Jane Lindsay Rawene Primary – Maria Barnes Kohukohu School – Tanya Filia Oromahoe School – Annie McGlone Umawera School - Christine Gilmore Matihetihe School - Doug Waima School Jenny | Minutes of F2F meeting |

1.2.2.A Report on your progress towards achieving the first of your elected programme goal

| Goal 1 To implement the New Zealand Curriculum / Te Marautanga o Aotearoa: through the use of e-learning | Cluster Programme Goals To improve student's learning through e-learning, especially numeracy and literacy, by focusing on the integration of ICT and inquiry based learning in an authentic context and meeting the requirements as stated in the NZ Curriculum / Te Matautanga o Aotearoa | Success Indicators Students/teachers are confident/competent in using ICT tools eg. Interactive online programmes (Mathletics) Evidence: Unit planning shows ICT integration, observation, mentoring meetings |
| --- | --- | --- |

Mid-year review

a. What progress has been made towards achieving these goals?

- KIS- We had up to two delegates from almost each school within our cluster attend the e-learning conference in Rotorua during term one of this year. Professional feedback logs were kept for the workshops attended and in some cases posted on our wiki site.

- Kohukohu - Unit  planning has ICT integration with themes for term 1 & 2, included in each appraisal for staff members. Staff using E-Tap to plan and assess.  Assessment and monitoring timetable includes ICT sample for portfolio samples, E-tap data entries included on monitoring timetable. School wide policy on internet use for our students and staff reviewed at BoT meeting

- All schools are utilising the expertise of our ICT cluster Facilitator to assist teachers and raise student engagement in all curriculum areas, especially literacy through the use of ICT tools and software.

- KES - Robin from Kaikohe East is keen to integrate authentic learning into her bi-lingual programme. After attending Karen Boyes workshop at L@S Robin is using some to the ideas in her classroom. Her Conference feedback can be viewed at this link.  Karen Boyes - Teaching in an Authentic Context

- Waima-Cluster leaders expertise used to assist staff in raising student knowledge across the curriculum.

KWS - Our new vision “Empowering Successful Learners Together” has provided a focus for our use of ICT at our school, encompassing many of the components of the NZC.Interactive whiteboards have been used in a variety of ways that increase Literacy and Numeracy skills. However, one of the major focuses has been on students taking greater responsibility for their learning by sharing it with their parents, teachers and peers. Boards have enabled learners to provide evidence on how they are currently achieving, identifying their next steps to learning and how they intend to get there. West Action Plan

Facilitator - The first term initially focussed on working with teachers to create individual ICT action plans, establishing school wide goals and a focus for each school.  The facilitator also began working with students to ascertain their level of knowledge and understanding in the use of ICT in their classroom programme and their level of skill.

b. What evidence supports this?

KIS: Ict professional learning goals have been incorporated into quality assurance and appraisal systems, ICT Committee has been formulated within schools to develop ICT school wide initiatives and focus. Staff meetings have been given a ICT PD slot every second week, the focus of this PD slot is set by the ICT committee and reflects cluster discussion and focus. Example of teacher Individual Action Plan  Kaikohe Intermediate Discussion Plan for Staff Meetings

Kohukohu-Our school strategic planning and annual goals show this evidence, support from facilitator to show a clear link to our cluster goals and our strategic planning. Strategic Plan

TS:  Staff meeting time is allocated to share ICT knowledge, activities and resources. There is a heightened awareness amongst staff to intergrate ICT in all curriculum areas. The laptops are being used every day - this was not happening last year. All students are now using the laptops in a range of curriculum areas. Our students are engaged in their learning when using the laptops. The data projectors are in use every day. These have been used used to explore maths and science websites,  AsTTle results have been shared with students on the projectors so students can understand and discuss their AsTTle test results. Students have set goals for themselves in maths, pangarau, writing, tuhituhi. We have explored and developed a list of useful websites for students to learn, and teachers  to teach, in te reo Maori.

KES - We have an ICT Team who meets weekly to determine next steps in terms of pd, budget purchases, attaining cluster/school/individual teacher goals and ensuring that we are beginning to engage students and teachers and not just use ICT as a tutu tool.  While it is difficult to ascetain whether ict will enhance student progress it has certainly turned on a few lights and is showing that children are more engaged and interested when ICT is included in their daily programmes.  New data projectors and cameras are being well used and staff who do not currently have a data/screen set up are envious of those who do. Minutes of Meeting 19th May

KWS - This was evident in our recent 3 way conferences where students took lead roles, with the support of their teacher, in our year 2/3 class. Therefore, enabling all participants to set realistic goals, and in the process, develop closer relationships with parents’ and whanau.

OPS - The facilitaor has worked with individual teachers and set action plans for professional development for the year plus worked with groups of children in each classroom on a variety of tasks involving ICT

Facilitator-It is evident from the facilitator's timetable and daily task sheet that time is spent working with students to improve their skill level and support them to support others in thier class and school to implement specific programmes decided on by the facilitator and LTs. An example of classroom use - Robin from KES  used ideas she took from her workshop at L@S to introduce authentic learning in her classroom.  In a recent lesson where students were looking at popular Maori songs, they asked who Eddie Lowe was. With her new  projector and screen in the class, Robin was able to instantly Google and find the singer for the students.  This instant, anywhere, anytime learning meant Robin was able to make what she was doing real and authentic.

Oromahoe school- ICT professional learning goals set as appraisal goals for each teacher, Teachers share their own ICT learning at staff meetings, students sharing their ICT learning at assemblies.  Example of Action Plan

Okaihau-Appraisals - schoolwide and individual goals set.  Greater use of students using cameras - powerpoint, photostories. Kate Action Plan

Facilitator - Evidence of working with Principals and teachers to set school wide goals and individual teacher plans is shown in the following examples.  Umawera School Action Plan  Example of teachers action plans are seen in the Oromahoe / Okaihau feedback.

c. What are the key lessons for the cluster?

KIS-Discuss share and contribute regularly, communicate visions and ideas in a very articulate manner, team PD is very productive as a cluster as pertinent conversations occur regarding the implementation of ICT into our learning programmes and curriculum.

Kohukohu-Sharing regularly via face to face meetings and facilitator visits to our school.  Be aware of the isolation of other schools in our cluster and set up audio conferencing and google docs as a cluster.  These have been implemented.

KES - Agree with all of the above

It is important for the facilitator to be seen, working with teachers and students, ensuring ICT is being integrated into daily planning practice.

OS - The benefits of a full time facilitator have led to rapid uptake of some applications.

Okaihau-share ideas and difficulites - problems associated with high ICT costs and working from small budget.

Facilitator - A key area is to continuously revisit the action plans, ensure teachers are being provided with the learning they require, introduce them to new and relevant resources for the needs in their classrooms.

d. What are the next steps towards achieving the outcome?

KIS-Incorporate the specific learning intentions (Knowledge and skills) more closely to our learning themes, sharing best practice ideas together as staffs and schools within our cluster to achieve this and identify some cluster best practice types of systems.

Kohukohu-Involving our board members to develop an ICT vision for our school and to ensure budgets are able to be used to best support our ICT goals.  Ensure our cluster ICT goals are shared with all staff and they are aware of these goals.

TS-Perhaps sharing of experiences, a great website or resource via the weekly newsletter.

KES-Looking towards more sharing of what schools within the cluster are achieving in a practical way through mini-conference perhaps.  Continuing to share cluster / school goals and progress staff individual action plans

For this year, the facilitator must continue to support teachers and students in the classroom to embedd the use of ICT for every student to have access to e-learning.

Okaihau-continued sharing of ideas and support from facilitator.

- Feedback from Matihetihe

1.2.2.B Report on your progress towards achieving the second of your elected programme goals

| National Goals Goal 2 Increase capability of teachers and principals to improve students' learning and achievement through e-learning | Cluster Programme Goals To ensure all staff will be using ICT pedagogy to develop life-long learners To develop a culture of e-learners that meets the individual needs of students with an emphasis on improving educational opportunities and achievement for Maori and Pacific Island students. To provide opportunities and time for professional learning, regarding the "new" approaches to pedagogy and curriculum, with an emphasis to viewing ICT not as a "tool", but as an environment for learning. To create a cluster of schools that empowers increased e-learning leadership and ICT strategic planning to meet the needs and capabilities of principals and teachers. | Success Indicators A baseline survey has been completed to indicate what we will need to be focusing on PD programmes are in place - reflecting the outcomes from survey · Evidence: PDP notebooks have been set up, reporting back forms have been filled in/established, feedback reports to BoT, staff mtgs are giving over time to PD, whiteboards are used for hot tips/new learning etc. · e-learning opportunities are negotiated with students · evidence that teachers planning reflects ICT Teachers are able to plan e-learning pathways based on their learning needs and desires · Evidence: classes have set up their own Wiki space, google docs are being used, resources, vocab building Professional readings are becoming a norm Interface magazine has been ordered and being utilised and information is being disseminated ICT PD newsletter is being shared on a regular basis at staff mtgs Evidenced: · Staff mtg. minutes, reference to prof readings, implementation of the PDP Journals, Prof record/documentation from the PF Our Lead team has been confirmed and the JD's have been signed Every school has an ICT strategic plan School budgets will reflect ICT as the focus Evidence: A cluster wiki has each schools strategic ICT plan uploaded into this space. |
| --- | --- | --- |

Mid-year review

a. What progress has been made towards achieving these goals?

A Monkey survey has been completed by all schools.  The results are attached.  Unfortunately not all teachers had access to the survey online to complete.  This meant only 44 out of 70 teachers actually completed the survey so the results are not really a clear reflection of what is happening across the cluster.  However, some of schools created their own surveys, so they could better understand the needs of their teachers when setting  school wide goals for ICT.

Kai-oro-hoki wiki set up and accessed by Principals and LTs for editing

Staff of cluster schools are streamlining systems to promote on-line communication modifying school systems to promote their own e-learning (Electronic school calendars/ staff meetings exploring software and equipment)

Kohukohu - Our facilitator has worked with our students in photostory, using the digital camera and utilising ICT tools we currently have.

TS - All Principals have a gmail account and google docs is being used - a learning curve for some of us.

KWS - Three training sessions with regional support facilitator, Rob Webb, have been used to use ETAP more efficiently in recording and presenting assessment information.

KWS - School wide electronic attendance registers have enabled closer monitoring, and the ability to set class and school wide targets. Therefore, issues and concerns are dealt with as soon as possible to ensure students are at school learning.

The use of ICT in developing a more efficient and well informed school has streamlined tasks to ensure that teachers have more time to focus on teaching & learning.

ETAP - New to ETAP - in school support from facilitator and attended 2 work shops with regional suuport facilitator Rob.  Data has now been recorded and staff are currently designing student report.

b. What evidence supports this?  Refer to photos below to see evidence of this happening in schools.

KIS -The cluster facilitator being used to enhance students use of technology within a classroom setting/incorporating specific software to enhance learning (Marvin/Comic Life/Photo story) PD journals kept to track PD-(Looking to develop digital portfolios in this area.

Kohukohu -Cluster facilitator working in classroom to set up photostory, used microphones with class, and the digital cameras.

TS: Our Charter and School Curriculum have goals and plans regarding ICT. We have appointed a Lead Teacher. Her job description has been agreed to. She has worked alongside staff to develop individual goals - short, medium and long term goals. Long term is to the end of the year as needs and knowledge change rapidly. Staff meeting time has been allocated for sharing of ICT professional development, activities, use of resources across curriculum areas, and developing our school wide goals as per our charter and curriculum. Before and after a school visit from our ICT Cluster Facilitator staff discuss needs and priorities in order to best utilize her expertise and time.

KWS - Due to this, quality reflection has occurred to help identify learning needs through the development of “Achievement Stories” for each class. The implementation of the School Calendar provides all timetabled information, which is easily accessible at home or within the school at any time, is always up to date and is maintained and the responsibility of all staff.

The facilitator sends out a weekly newsletter to all Principals / LTs so they are aware of the following weeks timetable and can prepare for facilitator visit, future dates to remember, feedback / pics form previous week and exciting sites to visit. Newsletter

Oromahoe school - all teachers are keen to be involved in any PD available and sharing their learning with others in staff meetings.  There is a buzz of excitement around new learning in the staffroom and the classrooms. ICT and e-learning in teachers' planning and negotiated with students.  Teachers share relevant bits from Interface magazine.

ICT and e-learning sits as a priority goal in our three year charter.

Okaihau-Students using comic life and photostory.  Powerpoint on enviromental journey.

KES - Evidence of teachers supporting students with e-learning in response to their needs.  Students engaged in learning, keen to write, enthused by video on You Tube, access to parents at home. Class wiki sites with individual pages for students, set up Term 2.  Evident from student input how they are engaged in their learning.

- Rangimarie

- Tumanako

c. What are the key lessons for the cluster?

KIS - Share experiences of software and tools to utilise time effectively (facilitators and time set aside for PD) Develop effective communication systems so mistakes are only made once in the cluster and not each school.

Kohukohu-Share success with others, bulk purchase ICT tools to save on costs of hardware.

TS - Support one another - those with expertise in software or  tools be willing to help others in the cluster - within reason.

As Facilitator, it is evident that all schools are at different levels of creating a culture of e-learners across the school.  I am working towards motivating and encouraging those who do not yet have infrastructure in place to ustilise what they do have and encourage the use of free software to engage students and demonstrate to teachers the benefits of using these programmes to enhance Literacy and numeracy.  We have had informal meetings and staff meetings on the use of these programmes and how to integrate into Literacy / Numeracy.

OS-Support each other in keeping the focus on learning across the curriculum - not just the whiz bang.

Okaihau-support and sharing of ideas - facilitator informing sharing ideas of what is avialable for high learning at low cost.

d. What are the next steps towards achieving the outcome?

KIS - Keep developing staff knowledge of software and technology through planned PD, provide learning opportunities for our students using systems that help their learning in class and is not reliant on constant supervision (Inquirers) Continue to build on a e-learning culture among our staff and cluster schools.

Kohukohu - Staff meetings specific focus on ICT professional development.  Facilitator to work, model effective ICT practice in classrooms for teachers to observe and implement themselves, facilitator to attend TOD and staff meetings with staff around effective ICT practice. ICT infrastructure analysis of individual schools by NorthCom

To develop Literacy and Numeracy as a focus when using software, the next step is to ensure ICT and e-learning are integrated into term and daily planning. This can be achieved by the facilitator regulary visiting individual action plans with each teacher and sharing good ideas across the cluster.

Teachers are so keen to move forward, it is hard to keep up.  Every school has e-learning happening and at this stage there is something specific to each school, which will make for a wonderful sharing day in Term 4.

Okaihau-ICT PD - what will be relevant and affordable for our school.

OS-Consolidate the new learning so that it becomes not just a tool but an environment for learning.

1.2.3   Report on your programme implementation during the milestone period

a. Programme Implementation

| Programme Professional Development Activities | Who was involved and how many were involved? |
| --- | --- |
| Individual School responsibility Baseline Survey Data Cluster Launch - for all teachers, to introduce the vision and goals of the contract Management Meetings Lead Teachers Roles and Responsibilities Cluster Meeting / LTs and Principals Setting up infrastructure in schools Enhance Literacy and Numeracy through PD programmes | A 10 question Monkey Survey was set up for all schools to respond to by a given date. Unfortunately, there were some technical difficulties for some schools and there were only 44 responsed instead of the explected 70. However it was clear from the responses that we needed to show the Cluster Goals more clearly. Response to Question 2 From the responses to Question 1, we were able to ascertain that most teachers were aware of the focus of ICT for their school, where they would like to see it developed in their school and how they see it being used across the school. Responses to Question 1 Question 3 asked teachers For the first term of the contract the Facilitator worked with individual teachers to set up Action Plans of what ICT PD they would like to achieve for themselves and their students. This is ongoing as teachers are becoming confident with some of the programmes they were unsure of. This will be a working document, for them to constantly change so they are upskilling themselves all the time. Of the 12 schools, the Facilitator worked with staff from 7 schools to create individual staff Action Plans, 3 schools LTs are developing Action Plans and 3 schools have created a school wide action plan. The facilitator and acting Host Principal led this day on 9th Feb. from 3.30pm - 5.30pm. Teachers from every school were represented. Using a PLOT Collegial Search, teachers were asked to align the National Goals with Cluster Goals. Four of the twelve Principals are also Lead teachers due to the size of their school. For this reason it is practical to hold management meetings after a Sharing or LT Day so everyone is available and saves another day travelling. We had a hui for everyone on the Thursday afternoon of the u L@S Conference. Here we discussed the possibility of a follow up meeting, with presentations, so everyone could come on board with infrastructure and hardware. Facilitator to organise this for our LT Day on 11th March. We also discussed feedback from Conference and agreed that Facilitator would create a Cluster Wiki and upload feedback. Kai-oro-hoki Cluster 5th March - Acting Host Principal and Facilitator met to discuss budget for conferences for staff for each school. During our combined Principal / Lead teacher meeting on Thursday 11th March, we reviewed the roles and responsibilities of LTs. There were changes made and sent to all schools for them to share with Principals and staff. 11th March - After a successful conference in Rotorua, schools were interested in speaking to companies about hardware and software suitable for their schools. Contact was made with reps from Mimio, Activ, Sitech, Gen-i and North Com to attend and present. This was very informative and schools have taken up the offer from North-com to quote and give feedback on infrastructure for their school. Schools are now waiting for results from this. First Cluster Meeting; Mimio Presentation. 25th March - Visit to Whangarei, Cluster Meeting 11 Principals / LTs travelled to Manaia View School. After an observation visit to classrooms and the Manaia View TV studio, we had a shared discussion. Host Principals and facilitator from a recedntly exited cluster spoke to the group about finances, resources and the importance of sharing. Each cluster introduced themselves so we can have shared contact over the next 3 years. LTs came back very excited with some ideas to introduce immediately into their schools. 21st April - F2F meeting with Kathe at Mid North Motor Inn. This was a very successful day, see minutes in Section 1. During this day we set those 10 Principals up with a g-mail account and introduced them to Google Docs. It was agreed to upload Milestone 1 to Google Docs and share with all Principals for their input. We have since set the remaing 2 Principals with their own g-mail. 13th May - LT Observation Day. This day was organised for LTs / Principals and BOT members to visit and observe ICT in action at schools who have been previously part of a cluster or integrate ICT into their classroom programmes. We visited 3 schools, using Activ Boards and Mimio boards and integrating ICT in curriculum areas across the school. 9 schools participated in this day, 2 schools brought along BOT members. In the afternoon we met at Northland College where Carolyn Bennett, e-learning Principal for Farnet demonstrated the use of video and audio conferencing. She also discussed the use of Moodle and how a LMS works. Carolyn has taken this a step further for us and agreed to work with Diane to set up a Moodle site for the cluster. We will work together on this to begin sharing across the cluster and the plan is to have it embedded across the whole cluster by 2012. Carolyn Bennett talking with LTs and Principals; Tanya Coutts, ECE facilitator sppeaking at the Whangarei Cluster Meeting. |
| How well were the programme activities carried out? How well were the programme activities carried out? Although the facilitator worked with Principals on the National/Cluster goals, it was evident from the Monkey Survey that teachers were not sure what the actual vision or goals of the cluster was - see question 2. These were then rewritten in a more familiar format for teachers and shared at our F2F meeting day. They have been digitally sent to all schools and most schools now have a copy visible for all staff to see - in their staffroom or appropriate place. Lead Teachers from each school have been given a copy of their roles and responsibilities. These will be followed up at each Cluster Sharing day to ensure they are For many teachers, it was a bit premature setting specific goals, as they did not know what they wanted. With discussion between the Facilitator and Lead teachers at each school it was decided which programmes to introduce and focus on. All schools looked at PhotoStory3, trialled ComicLife and 2 took up the offer from Marvin. Marvin Feedback - Matauri Bay The relevant programmes were introduced at staff meetings during term 1 or at workshops in 2 schools on call back days in the holiday break. At 2 schools the Facilitator worked alongside Teacher Aides, to determine thier needs to suport students they work with. This has been very beneficial at Kaikohe East where they have a Special Needs unit and teacher aides are now able to ustilise the digital cameras and programmes for use with their students. The Facilitator has also supported schools with their SMS, running staff meetings at 3 schools to demonstrate data input, retrieving data, creating custom reports, pupil lists and pupil records. In term 2 we have begun to work with students using these programmes, upskilling them to lead others and support teachers with their learning. The use of PhotoStory3, Comic Life, Movie Maker, and Marvin has been particularly successful. The focus is now on how these programmes can enhance Literacy and Numeracy. Every school is focused on the Cluster goal to engage students to enhance Literacy and Numeracy, so a major focus of what is implemented into the school ICT programmes is based around this. Students Using PhotoStory 3 - Rawene; Introducing students to Comic Life - Rawene. Staff meeting - Okaihau Matihetihe - Comic Life and Power Point; Teacher Aide training - Kaikohe East Matihetihe - using Google, research. Although the facilitator worked with Principals on the National/Cluster goals, it was evident from the Monkey Survey that teachers were not sure what the actual vision or goals of the cluster was - see question 2. These were then rewritten in a more familiar format for teachers and shared at our F2F meeting day. They have been digitally sent to all schools and most schools now have a copy visible for all staff to see - in their staffroom or appropriate place. Lead Teachers from each school have been given a copy of their roles and responsibilities. These will be followed up at each Cluster Sharing day to ensure they are For many teachers, it was a bit premature setting specific goals, as they did not know what they wanted. With discussion between the Facilitator and Lead teachers at each school it was decided which programmes to introduce and focus on. All schools looked at PhotoStory3, trialled ComicLife and 2 took up the offer from Marvin. Marvin Feedback - Matauri Bay The relevant programmes were introduced at staff meetings during term 1 or at workshops in 2 schools on call back days in the holiday break. At 2 schools the Facilitator worked alongside Teacher Aides, to determine thier needs to suport students they work with. This has been very beneficial at Kaikohe East where they have a Special Needs unit and teacher aides are now able to ustilise the digital cameras and programmes for use with their students. The Facilitator has also supported schools with their SMS, running staff meetings at 3 schools to demonstrate data input, retrieving data, creating custom reports, pupil lists and pupil records. In term 2 we have begun to work with students using these programmes, upskilling them to lead others and support teachers with their learning. The use of PhotoStory3, Comic Life, Movie Maker, and Marvin has been particularly successful. The focus is now on how these programmes can enhance Literacy and Numeracy. Every school is focused on the Cluster goal to engage students to enhance Literacy and Numeracy, so a major focus of what is implemented into the school ICT programmes is based around this. Students Using PhotoStory 3 - Rawene; Introducing students to Comic Life - Rawene. Staff meeting - Okaihau Matihetihe - Comic Life and Power Point; Teacher Aide training - Kaikohe East Matihetihe - using Google, research. |

b. Learning at School

The enthusiasm and positive feedback from the 23 Principals and Lead teachers who attended L@Schools has meant all staff are on board.  Each school gave verbal feedback to staff at staff meetings and workshop feedback can be viewed on our L@Schools Wiki Page on our Kai-oro-hoki Wiki.  The committment and positive attitude from those who went to conference has led to regular ICT meetings in schools, an ICT component at staff meetings in schools, excellent attendance at our combined cluster meeting day in Whangarei, and excellent attendance at our own cluster day for Principals and LTs.  Principals are discussing the advantages of sending staff to Rotorua. They are setting action plans to ensure staff have opportunities to attend conferences - not just LTs and Principals.

TS - As a result of attending the Learning@School Conference our teachers are motivated to use the ICT tools we have across the curriculum. We knew that ICT helps to engage our students but we need to be mindful that the engagement needs to be meaningful not just entertaining. We also need to work on creating a thinking culture in our school to enable our students develop 21st Century skills to help them cope in a rapidly changing world. Developing thinking across the whole school will ensure continuity and consistency and will help achieve a ‘culture of thinking'. - Julia Aitkin Workshop

Mary from Oromahoe has used Digital Imaging in the Classroom following on from L@S - here is her feedback from her workshop. Digital Imaging

Rangi from Matauri bay has been collecting maori resources after her workshop at Conference - Resources for Maori

Natasha from Matihetihe created some short clips for her feedback from Conference.

Digital Content

c. Changes to contact details

Chicky Rudkin - Kaikohe East School will work with Phil Gordon as Project Director

Disbursement schedule

| ICT Professional Development Cluster: |  | Kai-oro-hoki Cluster Kai-oro-hoki Cluster Kai-oro-hoki Cluster ICT Professional Development Cluster: |  |  |
| --- | --- | --- | --- | --- |
| Contract No. |  | Contract No. 10-0239 10-0239 10-0239 |  |  |
| Milestone No. |  | 1 1 1 Milestone No. |  |  |
| To: Neil Melhuish e-Learning Unit Ministry of Education PO Box 1666 WELLINGTON |  | From: From: From: To: Kaikohe Intermediate PO Box 252, Kaikohe Kaikohe Intermediate PO Box 252, Kaikohe Kaikohe Intermediate PO Box 252, Kaikohe Neil Melhuish e-Learning Unit Ministry of Education PO Box 1666 WELLINGTON |  |  |
| For Professional and Operational Costs: For Professional and Operational Costs: For Professional and Operational Costs: For Professional and Operational Costs: For Professional and Operational Costs: |  |  |  |  |
|  | 3yr Budget |  | 3yr Budget Actual-to-date |  |
| Professional Fees | $133,333.35 |  | $133,333.35 $ 18,132.73 | 13.6% |
| Professional & other Direct Costs | $ 80,000.01 |  | $ 80,000.01 $ 22,051.60 | 27.5% |
| Indirect Operating Costs | $ 13,333.35 |  | $ 13,333.35 $ 306.88 | 2.3% |
| Teacher Development Costs | $ 93,333.36 |  | $ 93,333.36 $ | 0% |
| Goods and Services tax | $ 39,999.99 |  | $ 39,999.99 $ 2,345.88 | 5.8% |
| Total | $360,000.00 |  | $360,000.00 $ 42,837.09 | 11.89% |

The budget funding schedule of your contract shows the value of individual school contributions that were pledged to allow your cluster programme to be implemented. Complete the following table and indicate if your schools’ contributions approximated those pledges. If not then provide an explanation of why not and how the cluster will ensure that shortfalls do not impact on the programme delivery.

| School Name | Amount Pledged | Contribution approximates amount pledged? Yes/No |
| --- | --- | --- |
| Kaikohe Intermediate | 1575.00 | Yes |
| Kaikohe West | 3325.00 | Yes |
| Kaikohe East | 1925.00 | Yes |
| Tautoro | 875.00 | Yes |
| Okaihau Primary | 1575.00 | Yes |
| Waima | 525.00 | Yes |
| Umawera | 350.00 | Yes |
| Rawene | 700.00 | Yes |
| Kohukohu | 350.00 | Yes |
| Matihetihe | 525.00 | Yes |
| Matauri Bay | 700.00 | Yes |
| Oromahoe | 700.00 | Yes |
| Total pledged | 13,125.00 |  |

When you have had your Milestone approved by your National Facilitator then you can email a PDF copy to:

ictpd.milestone@minedu.govt.nz